## Slide 1
25G MENTOR-MENTEE
TRAINING PLAN
  June 2017 – June 2019
Date: June 28, 2017
Mentee: Nhi Cao (1991)
Mentor: Thuy Tran (0505)
Software Tool Solution 1 Group
Software Engineer Division
Renesas Design Vietnam Co., Ltd.

## Slide 2: Agenda
Training Target Page 03
Current Status Page 05
Gaps Analysis and Solution Page 06
Training Plan Page 08
Commitment Page 09

## Slide 3: Training Target(1/2)
Target: Achieve role Level 2 of Engineer for test validation (software) by March, 2019
Ability to do e2 studio verification without support, if it is within certain degree of difficulty
Role | Skill | Description | Target Level
Engineer for test validation (software) | Test item extraction | - Extract test items from various specifications and design specifications. - Round up and integrate the extracted test items into test specifications. | Level 2
 | Testing | - Conduct tests according to the test specifications. - Round up the results of the tests and make a report. | Level 2
 | Failure analysis | - Locate the cause of any trouble and make analysis of its influences and other side effects - Find similar bugs | Level 2
 | Test environment construction | - Have knowledge of the development environment (compiler, debugger) and target environment ( CS+, e2 studio and their plug-ins) and conduct tests and evaluations. | Level 2
 | Validity verification | - Create system verification specifications from the use cases as viewed from the user application side and from the view point of uses such as high load environment, and conduct tests. | Level 2

## Slide 4: Training Target(2/2)
Common Skill | Target
Development Process | Understand and can follow Development process. Can do feedback by looking at result of work.
Communication | Can express idea to others. Can report status/issues/solutions to leaders.
Management Ability | Can make schedule and follow it. Can manage common risk for assigned tasks: private issues (health,…), technical issues (lack of experience in assigned fields),…
English | TOEIC 700

## Slide 5: Current Status
Role | Skill | Current status | Current Level
Engineer for test validation (software) | Test item extraction | - Can understand simple specifications. - Can create Test cases but not cover all contexts. | Level 1
 | Testing | - Can conduct test for simple modules. - Testing without following testing procedure. | Level 1
 | Failure analysis | - Can only detect simple bugs, cannot find out root causes | Level 1
 | Test environment construction | - Can set up simple environment. - Need support from Mentor to set-up complex environment | Level 1
 | Validity verification | - Can not do validity verification | Level 1

## Slide 6: Gaps Analysis and Solution(1/2)
Skill | Gap | Root Causes | Mentee’s action | Mentor’s action
Test item extraction | Lack of knowledge about abnormal and boundary cases | Don’t have much experiences about abnormal and boundary cases | -Investigate documents, analyze old test spec for comprehension -Ask Mentor for confirm knowledge and unclear points | Provide reference documents, sample PCL Give hints/tips to Mentee to investigate Check output and feedback
Testing | Cannot do the complicated test case | Comprehension about PCL is not good | -Inv existing pcl to get main test view points - Inv standard test procedure which was defined in team | Provide standard procedure for using environment of testing Give hints/tips to Mentee to conduct test Check output and feedback
Failure analysis | Cannot find the root causes of bugs | Lack of knowledge about Failure analysis | -Investigate old countermeasures report to know how to analyze bugs -Investigate side effects to check for similar bugs -Confirm output and unclear points with Mentor | Provide sample report. Give hints/tips to Mentee to analyze failure efficiently Check report and feedback

## Slide 7: Gaps Analysis and Solution(2/2)
Skill | Gap | Root Causes | Mentee’s action | Mentor’s action
Environment construction | Cannot set up environment which combine many plug-in inside | Don’t understand all component plug-ins | -Take notes important steps to create environment -Set-up environment based on Mentor's hints | - Provide reference documents - Check output and feedback
Validity verification | Can not do system validity as user view point | Don’t have basic knowledge about system validity | -Investigate about the system using User manual -Refer old test spec. to create sample test spec. -Confirm output with Mentor | - Provide reference documents, sample - Check output and feedback
English | Misunderstand some words in technical field | Lack of technical vocabularies | - Learning more technical vocabularies from documents and | - Explain context and meaning of any technical vocabularies that mentee confuses

## Slide 8: Training Plan – TestiNG SKILL
Skill: Test Environment Construction | 
Target: Level 1.5-Set up e2s Environment (simulator debug) without support Duration: May 2017 - Nov 2017 (6 months) Mentee's action: Investigate about the e2 studio and plug-ins Take notes important steps to create testing environment Set-up environment based on Mentor’s hints Mentor's action: Provide reference documents Check output and feedback Assigned task: e2 studio ticket verification | Target: Level 2-Set up e2s Environment (various hardware debug) without support Duration: May 2017 - Nov 2017 (6 months) Mentee's action: Take notes important steps to create testing environment Set-up environment based on Mentor’s hints Mentor's action: Provide reference documents Check output and feedback Assigned task: e2 studio regression test
Skill: Testing | 
Target: Level 1.5-Reported issues due to lack of knowledge less than 40% Duration: May 2017 - Nov 2017 (6 months) Mentee's action: Investigate old test report, bug report for comprehension Self-create test report, bug report Mentor's action: Provide old test report Give hints/tips to Mentee to conduct test Check output and feedback Assigned task: e2 studio ticket verification | Target: Level 2-Reported issues due to lack of knowledge less than 20% Duration: May 2017 - Nov 2017 (6 months) Mentee: Confirm unclear points in requirement spec. with Mentor Self-create test report, bug report Mentor: Give hints/tips to Mentee to conduct test Check output and feedback. Assigned task: e2 studio ticket verification

## Slide 9: Training Plan – Testing skill
Skill: Test item extraction | 
Target: Level 1.5-Create test spec. cover 75% of requirement spec. Duration: May 2017 - May 2018 (12 months) Mentee's action: Investigate documents, analyze old test spec. to get test viewpoint Confirm test viewpoint with mentor, then conduct creating test spec. Mentor's action: Provide reference documents, sample PCL Give hints/tips to Mentee to investigate Check output and feedback Assigned task: e2 studio ticket verification | Target: Level 2-Create test spec. cover 100% of requirement spec. Duration: May 2017 - May 2018 (12 months) Mentee's action: Ask Mentor for confirming knowledge and unclear points Mentor's action: Give hints/tips to Mentee to investigate. Check output and feedback Assigned task: e2 studio regression test
Skill: Failure analysis | 
Target: Level 1.5-Create test spec. cover 75% of requirement spec. Duration: May 2017 - May 2018 (12 months) Mentee's action: Confirm unclear points in requirement spec. with Mentor Investigate old test report, bug report for comprehension Self-create test report, bug report Mentor's action: Provide old test report Give hints/tips to Mentee to conduct test Check output and feedback. Assigned task: e2 studio ticket verification | Target: Level 2-Can analyze normal bug without support. Duration: May 2017 - May 2018 (12 months) Mentee's action: Self-create analysis failure report Confirm output and unclear points with Mentor Mentor's action: Give hints/tips to Mentee to analyze failure efficiently Check report and feedback Assigned task: e2 studio regression test

## Slide 10: Training Plan – testing skill
Skill: Validity verification | 
Target: Level 1.5-Create system verification specification with viewpoint of user with little support Duration: May 2017 - May 2018 (12 months) Mentee's action: Discuss test view points with mentor Investigate the related documents collected by mentor to create test specification and conduct system test Take investigation note for knowledge sharing Mentor's action: Provide referent documents and old test data to mentee Review output of mentee and feedback Assigned task: e2 studio ticket verification | Target: Level 2-Create system verification specification with viewpoint of user without support Duration: May 2017 - May 2018 (12 months) Mentee's action: Discuss test view points with mentor; Take investigation note for knowledge sharing Mentor's action: Provide referent documents to mentee Review output of mentee and feedback Assigned task: e2 studio regression test

## Slide 11: Training Plan – Common skill
Skill: Management Ability | 
Target: Can keep assigned schedule Duration: May 2017 - May 2018 (12 months) Mentee's action: Make schedule Mentor's action: Given experiences and tips for Mentee Confirm Mentee’s schedule | Target: Can keep schedule and raise alarm if necessary Duration: May 2017 - May 2018 (12 months) Mentee's action: Make schedule and define risk for each task Improve estimating ability base on previous works by collecting work data Mentor's action: Given experiences and tips for Mentee Confirm Mentee’s schedule and risk management table
Skill: Communication ability | 
Target: Can report his problem to supervisor Duration: May 2017 - May 2018 (12 months) Mentee's action: Report work status and get comments from Mentor (daily, weekly…) Refer to report of experience engineers Improve English Mentor's action: Check Mentee’s report and give comments frequently Monitor mentee’s improvement progress regularly, carefully and give advice (if any) | Target: Can report work status in his team Duration: May 2017 - May 2018 (12 months) Mentee's action: Report work status and get comments from Mentor (daily, weekly…) Improve English Mentor's action: Check Mentee’s report and give comments frequently. Monitor mentee’s improvement progress regularly, carefully and give advice (if any)

## Slide 12: Training Plan – common skill
Skill: IDE architecture
Target: Can understand IDE architecture Duration: May 2017 - May 2018 (12 months) Mentee's action: Take note for IDE knowledge got from IDE Verification tasks Mentor's action: Given some hints and experiences for Mentee
Skill: . Operating System
Target: Can understand objective Operating System of assigned product Duration: May 2017 - May 2019 (24 months) Mentee's action: Investigate OS document Take note for OS knowledge got from IDE Verification tasks Mentor's action: Given some hints and experiences for Mentee

## Slide 13: Training Plan – common skill
Skill: Development process
Target: Can do feedback by looking at result of work Duration: May 2017 - May 2019 (24 months) Mentee's action: Attend meeting to follow the process requirement Report activities to Mentor Mentor's action: Require Mentee to follow process in his work Monitor Mentee’s activities

## Slide 14: Commitment
Commitment result after 2 year:
  Achieve Level 2 for Test validation Engineer
  Tasks self-schedule ability.
  Ensure the quality of output and time management.
  Support to train new members join to project.

## Slide 15
Thank you for your attention